## Summary
Ha Noi
| Province | Total On Air Site | RAT | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19
| Ha Noi | 16 | 4G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0
|  | 11 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
North
| Province | Total On Air Site | RAT | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19
| Hai Phong | 3 | 5G | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hai Duong | 0 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hung Yen | 0 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thai Binh | 0 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Thai Nguyen | 0 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ninh Binh | 1 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Da Nang
| Province | Total On Air Site | RAT | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19
| Da Nang | 0 | 4G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3 | 5G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0

## Ha Noi Progress
[7 empty] | 4G |  |  |  | 5G | [8 empty] | Monitor
No | Province | Cluster | Site Name | OM Link Status | Pre Swap Scripts | Site Status | Plan On-air | On-air Day | On-air Time | Status | Plan On-air | On-air Day | On-air Time | Status | Post Swap Scripts | NSN->HW Neighbors | CQT Start Time | CQT Complete Time | Remark | NEName_New4G | NEName_New5G | NEname_Old_4G_NSN | batch | Vendor | Alarm（update on May 19 10:00)
1 | Ha Noi | Pilot | HN_GLM_CN_NINH_HIEP | Connected | Done | On Air | 2026-05-06 | 2026-05-06 | 16:47 | OK | 2026-05-06 | 2026-05-06 | 16:47 | OK | Done | Not Yet |  |  | 4G Swap+New 5G Building 2.6G | HNIPDG02 | HNIPDG02 | HN_GLM_CN_NINH_HIEP | batch1 | NSN
2 | Ha Noi | Pilot | HN_GLM_CN_NINH_HIEP_CRAN_2 | Connected | Done | On Air | 2026-05-11 | 2026-05-11 | 15:15 | OK | NA | NA | NA | NA | Done | Not Yet |  |  | 4G Swap | HNIPDG03 |  | HN_GLM_CN_NINH_HIEP | batch2 | NSN
3 | Ha Noi | Pilot | HN_GLM_NINH_HIEP_2_CRAN | Connected | Done | On Air | 2026-05-11 | 2026-05-11 | 18:05 | OK | NA | NA | NA | NA | Done | Not Yet |  |  | 4G Swap | HNIPDG14 |  | HN_GLM_NINH_HIEP | batch2 | NSN
4 | Ha Noi | Pilot | HN_GLM_CAU_DUONG | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:00 | OK | 2026-05-15 | 2026-05-15 | 18:00 | OK | Done | Not Yet | 2026-05-15 18:50 | 2026-05-15 20:24 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG01 | HNIPDG01 | HN_GLM_CAU_DUONG | batch3 | NSN | 45G,User Plane Fault,45G,IP Clock Link Failure
5 | Ha Noi | Pilot | HN_GLM_CONG_THON | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:00 | OK | 2026-05-15 | 2026-05-15 | 18:00 | 2 sectors OK, 1 is NOK due to CPRI issue | Done | Not Yet | 2026-05-15 18:00 | 2026-05-15 21:43 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG04 | HNIPDG04 | HN_GLM_CONG_THON | batch3 | NSN | 45G,User Plane Fault,5G,BBU CPRI Interface Error,5G,RF Unit Maintenance Link Failure
6 | Ha Noi | Pilot | HN_GLM_DINH_XUYEN_2 | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 14:50 | OK | 2026-05-15 | 2026-05-15 | 14:50 | OK | Done | Not Yet | 2026/5/15 17:00 | 2026-05-15 21:24 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG06 | HNIPDG06 | HN_GLM_DINH_XUYEN_2 | batch3 | NSN
7 | Ha Noi | Pilot | HN_GLM_DINH_XUYEN_3 | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:05 | OK | 2026-05-15 | 2026-05-15 | 18:05 | 2 sectors OK, 1 is NOK due to CPRI issue | Done | Not Yet | 2026-05-15 18:20 | 2026-05-15 19:46 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG07 | HNIPDG07 | HN_GLM_DINH_XUYEN_3 | batch3 | NSN | 45G,Transmission Optical Interface Error,5G,BBU CPRI Interface Error,5G,RF Unit Maintenance Link Failure
8 | Ha Noi | Pilot | HN_GLM_DUONG_HA | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:05 | 2 sectors OK, 1 is NOK due to CPRI issue | 2026-05-15 | 2026-05-15 | 18:05 | 2 sectors OK, 1 is NOK due to CPRI issue | Done | Not Yet | 2026-05-15 20:24 | 2026/5/15 22:24:00 sector C issue | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG08 | HNIPDG08 | HN_GLM_CAU_DUONG | batch3 | NSN | 4G,BBU CPRI Interface Error,4G,Cell Blocked,4G,Data Configuration Exceeding Licensed Limit,4G,RF Unit Maintenance Link Failure,5G,BBU CPRI Interface Error,5G,RF Unit Maintenance Link Failure
9 | Ha Noi | Pilot | HN_GLM_DUONG_HA_2 | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:10 | OK | NA | NA | NA | NOK due to CPRI issue | Done | Not Yet | 2026-05-15 19:10 | 2026-05-15 20:24 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG09 | HNIPDG09 | HN_GLM_DUONG_HA_2 | batch3 | NSN | 45G,User Plane Fault,5G,BBU CPRI Interface Error,5G,RF Unit Maintenance Link Failure
10 | Ha Noi | Pilot | HN_GLM_HA_HUY_TAP | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:10 | 2 sectors OK, 1 is NOK due to CPRI issue | NA | NA | NA | NOK due to CPRI issue | Done | Not Yet | 2026-05-15 21:35 | 2026/5/15 22:10:00. 4G sector C locked | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG10 | HNIPDG10 | HN_GLM_YEN_THUONG_CRAN | batch3 | NSN | 45G,User Plane Fault,5G,BBU CPRI Interface Error,5G,RF Unit Maintenance Link Failure,BBU CPRI Optical Module or Electrical Port Not Ready
11 | Ha Noi | Pilot | HN_GLM_LA_COI | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 16:08 | OK | 2026-05-15 | 2026-05-15 | 16:08 | OK | Done | Not Yet | 2026-05-15 23:35 | 2026-05-16 00:58 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG11 | HNIPDG11 | HN_GLM_LA_COI | batch3 | NSN | 5G,BBU CPRI Interface Error,45G,User Plane Fault
12 | Ha Noi | Pilot | HN_GLM_NGA_4_NINH_HIEP | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 16:08 | OK | 2026-05-15 | 2026-05-15 | 16:08 | OK | Done | Not Yet | 2026-05-15 23:15 | 2026-05-15 23:55 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG12 | HNIPDG12 | HN_GLM_NGA_4_NINH_HIEP | batch3 | NSN | 45G,User Plane Fault,45G,IP Clock Link Failure
13 | Ha Noi | Pilot | HN_GLM_NINH_HIEP | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 15:30 | OK | 2026-05-15 | 2026-05-15 | 15:30 | OK | Done | Not Yet | 2026-05-15 17:00 | 2026-05-15 22:50 | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG13 | HNIPDG13 | HN_GLM_NINH_HIEP | batch3 | NSN
14 | Ha Noi | Pilot | HN_GLM_XUAN_DUC | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:10 | OK | NA | NA | NA | NOK due to CRPI issue | Done | Not Yet | 2026-05-15 22:00 | 2026/5/15 22:00:00 No 5G | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG21 | HNIPDG21 | HN_GLM_CAU_DUONG | batch3 | NSN | 45G,Transmission Optical Interface Error,45G,User Plane Fault
15 | Ha Noi | Pilot | HN_GLM_YEN_THUONG | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:13 | OK | 2026-05-15 | 2026-05-15 | 18:13 | OK | Done | Not Yet | 2026-05-15 20:19 | 2026/5/15 21:50:00 Cannot camp on 5G | Swap 4G + Newbuild 5G Single 2.6 32T | HNIPDG22 | HNIPDG22 | HN_GLM_YEN_THUONG_CRAN | batch3 | NSN | 5G,BBU CPRI Interface Error,5G,gNodeB Out of Service,5G,NR DU Cell TRP Unavailable,5G,RF Unit DC Input Power Failure,5G,RF Unit External Power Supply Insufficient,5G,RF Unit Maintenance Link Failure
16 | Ha Noi | Pilot | HN_GLM_YEN_THUONG_CRAN | Connected | Done | On Air | 2026-05-15 | 2026-05-15 | 18:13 | OK | 2026-05-15 | 2026-05-15 | 18:13 | OK | Done | Not Yet | 2026-05-15 19:00 | 2026-05-15 20:19 | Swap 4G | HNIPDG22 |  | HN_GLM_YEN_THUONG_CRAN | batch3 | NSN | 5G,BBU CPRI Interface Error,5G,gNodeB Out of Service,5G,NR DU Cell TRP Unavailable,5G,RF Unit DC Input Power Failure,5G,RF Unit External Power Supply Insufficient,5G,RF Unit Maintenance Link Failure

## North 5G Progress
[5 empty] | 3.8G_N77 |  |  | 2.6G_N41 | [7 empty] | Monitor
No | Province | Site Name | OM Link Status | Site Status | Plan On-air | On-air Day | On-air Time | Plan On-air | On-air Day | On-air Time | Post Swap Scripts | NSN->HW Neighbors | CQT Start Time | CQT Complete Time | Remark | NEName_New | NEname_Old | Batch | Vendor | Alarm（update on May 19 10:00)
1 | Hai Phong | HPG_CHI_DONG_BAI |  | On Air |  |  |  | 2026-04-29 | 2026-04-29 | 19:00 |  |  |  |  | Newbuild 5G Dual (2.6 64T + 3.8 64T) | HPGCHI02_5G | HPG_CHI_DONG_BAI_4G | batch1 | HUA
2 | Hai Phong | HPG_TNN_TT_HANH_CHINH_2_01R |  | On Air |  |  |  | 2026-05-07 | 2026-05-07 | 15:50 |  |  |  |  | Newbuild 5G Dual (2.6 64T + 3.8 64T) | HPGTNN57_5G | HPG_TNN_TT_HANH_CHINH_2_4G | batch1 | HUA | 5G,RF Unit DC Input Power Failure,5G,RF Unit Maintenance Link Failure
3 | Hai Phong | HPG_CHI_CAT_BA_4 |  | On Air |  |  |  | 2026-05-07 | 2026-05-08 | 9:30 |  |  |  |  | Newbuild 5G Single 2.6 32T | HPGCHI07_5G | HPG_CHI_CAT_BA_4_4G | batch1 | HUA
4 | Hai Phong | HDG_CGG_DUC_CHINH_3 | [5 empty] | NA | [6 empty] | Newbuild 5G Single 2.6 32T | HPGVHA10_5G | HDG_CGG_DUC_CHINH_3_4G | batch1 | HUA
5 | Hung Yen | HYN_VLM_CHI_DAO_2 | [5 empty] | 2026-05-18
6 | Thai Nguyen | TNN_PBH_THUONG_DINH_2 | [5 empty] | 2026-05-18
7 | Hai Duong | HDG_CGG_CAM_DINH | [5 empty] | 2026-05-18
8 | Hai Duong | HDG_CGG_CAM_GIANG_2 | [5 empty] | 2026-05-18
9 | Hai Duong | HDG_CGG_CAM_PHUC | [5 empty] | 2026-05-18
10 | Hai Duong | HDG_CGG_CAM_VU | [5 empty] | 2026-05-18
11 | Hai Duong | HDG_CGG_CAO_AN | [5 empty] | 2026-05-18
12 | Hai Duong | HDG_CGG_CAO_AN_2 | [5 empty] | 2026-05-18
13 | Hung Yen | HYN_YMY_LIEU_XA_3 | [5 empty] | 2026-05-18
14 | Thai Binh | TBH_DHG_DONG_XUAN | [5 empty] | 2026-05-18
15 | Ninh Binh | NB_GVN_GIA_SINH_2 | [5 empty] | 2026-05-18 | 2026-05-18 | 16:37 | [5 empty] | NBHTHL03_5G

## Middle Swap Progress
[7 empty] | 4G |  |  |  | 5G | [8 empty] | Monitor
No | Province | Cluster | Site Name | OM Link Status | Pre Swap Scripts | Site Status | Plan On-air | On-air Day | On-air Time | Status | Plan On-air | On-air Day | On-air Time | Status | Post Swap Scripts | NSN->HW Neighbors | CQT Start Time | CQT Complete Time | Remark | NEName_New4G | NEName_New5G | NEname_Old_4G_NSN | batch | Vendor | Alarm（update on May 18 15:00)

## Middle 5G Progress
|  |  | Hoang Van Gia Toan 60079944 |  | 3.8G_N77 |  |  | 2.6G_N41 |  |  |  |  | Pham Duy Thanh 60118201 | Pham Duy Thanh 60118201 |  | Monitor
No | Province | Site Name | OM Link Status | Site Status | Plan On-air | On-air Day | On-air Time | Plan On-air | On-air Day | On-air Time | Post Swap Scripts | NSN->HW Neighbors | CQT Start Time | CQT Complete Time | Remark | NEName_New | NEname_Old | Batch | Vendor | Alarm（update on May 18 15:00)
1 | Da Nang | DNNH26 | Connected | On Air |  |  |  | 2026-05-26 | 2026-05-16 | 16:15 |  |  |  |  | Newbuild 5G Single 2.6 32T | DNGNHS43-5G |  |  | HUA
2 | Da Nang | DNNH2B | Connected | On Air |  |  |  | 2026-05-26 | 2026-05-16 | 15:15 |  |  |  |  | Newbuild 5G Single 2.6 32T | DNGNHS48-5G |  |  | HUA
3 | Da Nang | DNTK01 | Connected | On Air |  |  |  | 2026-05-23 | 2026-05-17 | 15:47 |  |  |  |  | Upgrade to 5G Dual (Existing 3.8 + 2.6 64T) | DNGTKE02_5G |  |  | HUA

## South 5G Progress Tracker
[5 empty] | 3.8G_N77 |  |  | 2.6G_N41 | [7 empty] | Monitor
No | Province | Site Name | OM Link Status | Site Status | Plan On-air | On-air Day | On-air Time | Plan On-air | On-air Day | On-air Time | Post Swap Scripts | NSN->HW Neighbors | CQT Start Time | CQT Complete Time | Remark | NEName_New | NEname_Old | Batch | Vendor | Alarm（update on May 18 15:00)
1 | Hai Phong | HPG_CHI_DONG_BAI |  | On Air |  |  |  | 2026-04-29 | 2026-04-29 | 19:00 |  |  |  |  | Newbuild 5G Dual (2.6 64T + 3.8 64T) | HPGCHI02_5G | HPG_CHI_DONG_BAI_4G | batch1 | HUA
2 | Hai Phong | HPG_TNN_TT_HANH_CHINH_2_01R |  | On Air |  |  |  | 2026-05-07 | 2026-05-07 | 15:50 |  |  |  |  | Newbuild 5G Dual (2.6 64T + 3.8 64T) | HPGTNN57_5G | HPG_TNN_TT_HANH_CHINH_2_4G | batch1 | HUA | 5G,RF Unit DC Input Power Failure,5G,RF Unit Maintenance Link Failure
3 | Hai Phong | HPG_CHI_CAT_BA_4 |  | On Air |  |  |  | 2026-05-07 | 2026-05-08 | 9:30 |  |  |  |  | Newbuild 5G Single 2.6 32T | HPGCHI07_5G | HPG_CHI_CAT_BA_4_4G | batch1 | HUA
4 | Hai Phong | HDG_CGG_DUC_CHINH_3 | [5 empty] | NA | [6 empty] | Newbuild 5G Single 2.6 32T | HPGVHA10_5G | HDG_CGG_DUC_CHINH_3_4G | batch1 | HUA
5 | Hung Yen | HYN_VLM_CHI_DAO_2 | [5 empty] | 2026-05-18
6 | Thai Nguyen | TNN_PBH_THUONG_DINH_2 | [5 empty] | 2026-05-18
7 | Hai Duong | HDG_CGG_CAM_DINH | [5 empty] | 2026-05-18
8 | Hai Duong | HDG_CGG_CAM_GIANG_2 | [5 empty] | 2026-05-18
9 | Hai Duong | HDG_CGG_CAM_PHUC | [5 empty] | 2026-05-18
10 | Hai Duong | HDG_CGG_CAM_VU | [5 empty] | 2026-05-18
11 | Hai Duong | HDG_CGG_CAO_AN | [5 empty] | 2026-05-18
12 | Hai Duong | HDG_CGG_CAO_AN_2 | [5 empty] | 2026-05-18
13 | Hung Yen | HYN_YMY_LIEU_XA_3 | [5 empty] | 2026-05-18
14 | Thai Binh | TBH_DHG_DONG_XUAN | [5 empty] | 2026-05-18
15 | Ninh Binh | NB_GVN_GIA_SINH_2 | [5 empty] | 2026-05-18 | 2026-05-18 | 16:37 | [5 empty] | NBHTHL03_5G